## Sheet1
2019-11-05
General Election
Ninety (90) Days Prior |  | Completed
Order Election Materials from SBE
Notify Polling places that an Election will be held - LEE
Make sure Ballot proofs have been approved by Elect
Calculate Ballots needed for this election
Order Ballots from ESO
Send OVO & OVI Passwords to Matt for programming
Update LANCOVA website
Sixty (60) Days Prior |  | Completed
Notify OEs of assignments to work and training dates
Order Ballots from ESO (if not already done so)
Publish Notice of AB Voting days and hours and Final Reg. Dates
Post notice of Election at courthouse
Schedule programming of CAP machines for Absentee Voting
Prepare AB folders for In-Person Voting
Photocopy all Annual and FPCA AB apps and put in folders
Prepare SORS for CAP
Meet with EB (LEE) to assign Election Officers to Precincts
IN VERIS Do the following 3 steps
1. In VERIS do “Poll Copy”
2. Then set Ongoing Ballots
3. Then set Ballot Ready Date
48 -50 DAYS Prior
Received Ballots date:______________
L&A Testing and Programing date:
AB Voting BEGINS : | 2019-09-20
Absentee Voting Materials for Office & CAP:
Print the following before AB voting begins:
o In-Person AB Pollbook
o Mailed file logs for each precinct
o Provisional Ballot Log
o Accountability Forms and Seals
o CAP SORS
45 Days Continued |  | ü When Completed
Appoint Election Officials to serve at precincts
Schedule Training Date for officers
Send notices to these officials
Post signs in office of last day to register
Print Denial Notices for Registrations to include in letters
Twenty (20) Days Prior |  | ü When Completed
Send Notices to Party Chairmen to notify them of machine programming |  | Lee
Prepare Precinct Election Carts
Charge IPADs
Prepare Unofficial Results sheets
Prepare Precinct SORs if not already done
Prepare Judges Binders
CAP Specific Binder: SORS for CAP / Mailed AB Pollbook / Rejected & Unused Logs
Ten to Fifteen Days Prior |  | ü When Completed
Verify all OEs have up to date Oaths on file / Take Oaths to Training if needed
Hold Training for OEs
Notify SBE of Completion of Training (Form SBE 115)
Send Notice of Canvass to Courthouse for posting
Prepare Election Day Contacts and Phone List
Format all USB Flash Drives for EPBs
Run reports of # of Registered Voters
Prepare / finalize Chief Notebooks and accordion files
Call Tom and remind him of working Monday & Wednesday for Machines
Run an Alpha List from VERIS
Friday or Saturday Before Election |  | ü When Completed
Fill out and prepare receipt for Ballots and put on each clipboard
Prepare Clipboards for Judges
Package and Seal ballots for each precinct
Make copies of AB apps
At End of Day: Run Locality Pollbook from VERIS
Scan or Copy all AB applications via Mail
Download PaperPollbook files from VERIS and save to thumbdrive
Monday Before Election |  | ü When Completed
Immediately Run Locality Pollbook from VERIS if not done Saturday
Immediately Create PollBook Election and load on all flashdrives
Run Final AB reports
Sign and separate all Final AB Reports for precincts / attach to clipboards
Contact Glenn and remove Auto Attendant on PHONES
Get Secretary to sign any Emergency Ballots
Go to Post Office to pick up ballots / Count all ballots received back in mail and log this number on CAP SORs and any other blue boxes that need updating
Update XL Ballot tracker log with any entries for today (Emergency or Mailed ballots received) Print off copy for CAP officers
Close CAP EPB after 3 Pm and attach close summary to all daily OVI / OVO / EPB reports.
If any ballots are receive by mail/ update in VERIS and re-run CAP Final AB Report
Election Day |  | ü When Completed
Have What ifs / OVO and OVI open and close directions by phone
Organize Returned Mail Ballots for CAP
Go to Post Office by 3PM for final mail pick up of any ballots – Give to CAP
- Mark / Update Final AB Report
- Mark / Update XL Ballot Tracker (reprint for CAP officers if necessary)
- Mark / Update CAP SORs
Have Unofficial Results sheet by phone on or before 7pm
Enter Results in VERIS
Day After the Election |  | ü When Completed
Retrieve USB flash drives from EPB carts and Upload data into PAM
Run PAM reports
Upload voter credit into VERIS
Sort all Election Envelopes / Gather #2s for Canvass
Seal any Extra unused ballots in extra Envelope #6
CANVASS / Provisional Ballot Meeting 11:00 am (GREB19)
AFTER Canvass:
Enter any Provisional vote changes into VERIS (May take until Friday of the week before completed)
Enter VERIS Turnout totals
Seal and take ALL Election Materials to Clerk on or before end of day
Prepare Abstracts for signatures (4 -5 copies)
After the Election |  | ü When Completed
Type up / calculate Officer of Election Compensation and give to Betty
Type up Polling Place Donations and give to Betty
Type up and prepare pay for Machine Custodian
Distribute Abstracts to Clerk / Crystal / Files
Finalize Election Summary and print a copy of file and for Don (BOS)
Compare VERIS turnout and error reports to ensure correctness
Once State Approves Abstracts, Mail hard copies
Scan and send Abstracts to State Board via formsite
Enter all Rejected ABs into VERIS and send letters
Enter all Provisional Rejects and Send Letters
Send Provisional Accepted Voter Letters
File 1 Ballot of each Style in EB Appendices
File Statement of Printer, etc. in EB Appendices
File 1 Copy of Abstracts in EB Abstract Book
LOCAL Elections
Type up Certificate of Winners